## Sheet1
| Task | Deadline | Status | Comment | Estimated hours | Actual hours spent
Week 1 - Skeleton | Set up version control | 2010-10-17 |  |  | 1 | 3
| Set up web space with access for everyone | 2010-10-17 |  |  | 1
| Create and upload "hello world" to webspace | 2010-10-18 |  | Waiting on Snir | 1
| Create paper prototype of navigational flow for "setting an alarm" | 2010-10-18 |  |  | 2 | 2.5
| Code up screen place holders for "setting an alarm" | 2010-10-19 |  |  | 2
| Test site from mobile device | 2010-10-20
| Submit assignment | 2010-10-21
Week 2 - Functionality
| Fill out "setting an alarm" screens with functional content (buttons etc) | 2010-10-23 |  |  | 2
| Connect screens for "setting an alarm" with back-end. | 2010-10-26 |  |  | 4