## OEP_Plan
| Task | Deadline | Status | Comment | Estimated hours | Actual hours spent | Person
Sections |  |  |  |  | 7 | 0
| Sales & Marketing | 2012-12-10 |  |  | 0 | 0 | GC
| Partnerships | 2012-12-10 |  | Start with Business Canvas | 2 | 0 | VP
| Distribution | 2012-12-10 |  |  | 2 | 0 | VP
| Costs | 2012-12-10 |  |  | 1 | 0 | GC
| Revenue Model | 2012-12-10 |  |  | 1 | 0 | GC
| Funding | 2012-12-10 |  |  | 1 | 0 | GC
Submit |  |  |  |  | 5 | 0
| OEP written report | 2012-12-12 |  |  | 2 | 0 | GC | VP to review
| Slideshow | 2012-12-12 |  | Slideshow or Video will do | 2 | 0 | GC | VP to review
| Video | 2012-12-12 |  |  | 0 | 0 | GC
| Submit assignment | 2012-12-13 |  |  | 1 | 0 | GC

## Market_Plan
| Task | Deadline | Status | Comment | Estimated hours | Actual hours spent | Person
Mock-up |  |  |  |  | 8 | 8
| Set up Fieldtest account | 2012-10-24 |  |  | 1 | 1 | VP
| Create Fliptab space | 2012-10-24 |  |  | 1 | 1 | VP
| New Mock-up | 2012-11-26 |  |  | 4 | 4 | VP
| E-mail sign-up | 2012-11-26 |  |  | 2 | 2 | VP
| Testing | 2012-11-27 |  |  | 1 | 1 | VP | GC to review
Marketing |  |  |  |  | 8 | 6 | GC
| Create Marketing Plan | 2010-10-24 |  |  | 4 | 2 | GC | VP to review
| Execute marketing Plan | 2010-11-01 |  |  | 4 | 4 | GC
Submit |  |  |  |  | 8 | 7
| Write-up results | 2010-11-02 |  |  | 2 | 1 | GC | VP to review
| Write-up Marketing Page | 2010-11-02 |  |  | 2 | 4 | GC | VP to review
| Set up Prezi account | 2010-11-02 |  |  | 1 | 1 | GC | Did not use Prezi
| Create video / presentation | 2010-11-02 |  |  | 2 | 1 | GC | VP to review
| Submit assignment | 2010-11-03 |  |  | 1 | 1 | GC

## OAP_Plan
| Task | Deadline | Status | Comment | Estimated hours | Actual hours spent | Person
Mock-up |  |  |  |  | 10 | 11
| Set up Easel account | 2012-10-10 |  |  | 1 | 1 | GC
| Create Fliptab space | 2012-10-11 |  |  | 1 | 1 | GC
| Example 1: Broadsheet | 2012-11-14 |  |  | 2 | 1 | VP
| Example 2: Mid market | 2012-11-14 |  |  | 3 | 3 | VP
| Example 3: Tabloid | 2012-11-14 |  |  | 3 | 5 | GC
| Testing | 2012-11-14 |  |  | 1 | 1 | GC
Interviews & Survey |  |  |  |  | 21 | 14 | VP/AA/GC
| Create Evaluation Plan | 2010-10-17 |  |  | 1 | 1 | GC
| Create User Test Written Instructions | 2010-10-17 |  |  | 1 | 1 | GC
| Create Survey | 2010-10-15 |  |  | 3 | 2 | VP/GC
| Conduct face-to-face Tests | 2010-10-19 |  |  | 15 | 9 | VP/AA/GC (5 each)
| Conduct online survey | 2010-10-17 |  | Link to Facebook, Twitter and LinkedIN | 1 | 1 | VP/AA/GC
Submit |  |  |  |  | 7 | 6
| Write-up results | 2010-10-20 |  |  | 2 | 2 | VP/AA/GC
| Write-up report | 10/20/2012 |  |  | 2 | 2 | GC
| Create video | 10/20/2012 |  |  | 2 | 2 | GC
| Submit assignment | 2010-10-21 |  |  | 1 | 0 | GC

## Interview_Results_gc
| Question | Michael Mills | Sean Gilmour | Philomena Hagan | Paul Burrows | Rosemary Porter
1 | How do you access online news today?
| Google News |  |  |  | X
| Newspaper web site | Irish Times |  | The Telegraph | Guardian, Independent | Belfast Telegraph
| TV web site |  | BBC, RTE | RTE, BBC | BBC
Twitter
Facebook
LinkedIn
| Other |  | Wikileaks
Cryptome.org
2 | What do you like most about online news services currently available? | Free | Breadth of Info | When restricted for time or abroad it is a good way to catch up with news | Snippets of news | Good for when I haven't bought a newspaper
|  | Relevant to country I live in | Predict a situation based on headlines |  | Environmental news
Instant access
3 | What changes would most improve accessing news online? | Get relevant parts in front of me. | Local reporting | Fresh news | Already user friendly | Sites are usually too cluttered - I would like to make them simple
|  | More domestic / local news. | More diverse reporting | Crosswords / Puzzles
Opinion to drill down.
4 | How likely would use a personalized news service?
| Extremely likely | X
| Very likely |  |  | X | X
| Moderately likely |  |  | X
| Slightly likely |  |  |  |  | X
| Not at all likely |  | X
5 | If our new personalized news service were available today, how likely would you be to use it instead of competing services currently available from other sources?
| Extremely likely | X
| Very likely |  |  |  | X
| Moderately likely |  |  | X
| Slightly likely |  |  |  |  | X
| Not at all likely |  | X
6 | If you are not likely to use a personalized news service, why not?
| Do not need a service like this |  | X (News is already too biased) | X (too narrow)
Do not want a service like this
satisfied with competing services currently available
cannot pay for a service like this
| Not willing to pay for a service like this | X |  |  | X | X
7 | How important is personally preferred news content when accessing news online?
Extremely important
| Very important |  |  |  | X
| Moderately important |  |  |  |  | X
| Slightly important |  |  | X
| Not at all important |  | X (Outliner stories are filtered out)
8 | What would make you more likely to use a personalized new service? | Instant relevant. | Timely information. | Breadth of coverage | When I don't have time to read newspapers | Local news services plus if going abroad would like news of that place
|  | The way I think. |  | Worried about missing out on something
9 | If our new service were available today, how likely would you be to recommend it to others?
| Extremely likely | X
| Very likely |  |  |  | X
| Moderately likely |  |  |  |  | X
| Slightly likely |  |  | X
| Not at all likely |  | X

## Interview_Results_vp
| Question | Biljana Stangeland | Astrid Høst | Goran Dostanic | Marthina Blom
1 | How do you access online news today? | Internet | Internet, newspaper
Google News
| Newspaper web site | VG, Dagbladet | Aftenposten, Le Monde, France24 | VG, Politika, Blic | Guardian, Independent, Herald
| TV web site | NRK1 | TV5, 3, TV2 | BBC, NRK1, CNN | BBC, RTE
Twitter
| Facebook | Yes, not so often
| LinkedIn | Yes, not so often
| Other | B92.net, SerbianCafe.com
2 | What do you like most about online news services currently available? | Up-to-date, Free | Breadth of Info | The same I hate, too much information | Headlines
|  | Relevant to country I live in |  |  | Availability
3 | What changes would most improve accessing news online? | Relevant information based on my interests | Mobile device offline reading | Filter out the information I dont care about | Unobstructive layout, easy navigation on iPad
|  | Short summaries |  | No flashy ads
4 | How likely would use a personalized news service?
| Extremely likely | X
| Very likely |  |  | X (if solves multilanguage issue) | X
| Moderately likely |  | X
Slightly likely
Not at all likely
5 | If our new personalized news service were available today, how likely would you be to use it instead of competing services currently available from other sources?
| Extremely likely | X
| Very likely |  |  | X | X
| Moderately likely |  | X
Slightly likely
Not at all likely
6 | If you are not likely to use a personalized news service, why not?
Do not need a service like this
Do not want a service like this
| satisfied with competing services currently available |  | X
cannot pay for a service like this
Not willing to pay for a service like this
7 | How important is personally preferred news content when accessing news online?
| Extremely important |  |  | X
| Very important | X | X
Moderately important
| Slightly important |  |  |  | X
Not at all important
8 | What would make you more likely to use a personalized new service? |  | Timely information. | Configuration | Offline reading, archiving option
Multilanguage
9 | If our new service were available today, how likely would you be to recommend it to others?
| Extremely likely | X
| Very likely |  |  | X | X
| Moderately likely |  | X
Slightly likely
Not at all likely

## Survey_Results
| Question | 28 Responses
1 | How do you access online news today? | Response Percent | Response Count
| Google News | 14.3% | 4
| Newspaper web site | 32.1% | 9
| TV web site | 25% | 7
| Twitter | 10.7% | 3
| Facebook | 28.6% | 8
| LinkedIn | 14.3% | 4
| Blogs | 14.3% | 4
| Other | 28.6% | 8 | Zite | Pulse | Yahoo | Bloomberg | Businessweek | MSN | BBC | NYT | WSJ
2 | What do you like most about online news services currently available? | It's easy and fast | It is free | The source- I trust my local and my national | They automatically come up in my news feed and are instantly accessible | Easy to glance at headlines and see what is going on. | Easy and fast access | The variety of formats available | Filtering, readyness | Its Live and upto date. | Can view news channels from around the world | accessible anytime anywhere and always up to date. | Accessablity | Readily available, mostly concise | To the point focused on very current affairs | Dedicated app | Google's personalisation | The combination of freshly updated news, and the ability to dig deeper with more extensive articles and analysis. | KNow my way around it, BBC reasonably unbiased, good coverage home and abroad | Quick updates, access to the same news on different media so that you can have different opinions on the same topic | There are only a few I trust to get it reasonably honest and straightforward. | its fast, broad and brief | Frequently updated
3 | What changes would most improve accessing news online? | it should be organized better | I check the news more times a day | My problem is that there are too many services to check out there, and 70-80% of the news are the same, but still you have to check every single website for that 20% that could be really interesting. Somehow a way to aggregate news from all frequently checked sources and filter out the duplicate news. | Aggregation from these sources of my choice types of stories. | A news feed that includes all the news channels and newspaper so readers do not need to surf this website or that. | RSS distribution through social networks | Ability to import feeds from different news sites on one story | better readers that are more customizable | making all free/nominal fee, instead of mandatory paid on line | Reduce advertising. Less formatting like a newspaper more like a summary document | App able to bring several sources | Ability to see Google news quicker on phone | The ability to access news through multiple channels - i.e. regardless of platform. | Clear lists of stories maybe with new ones flagged, clear categories | filtering out Kim Kardesian, Justin Bieber and verything about sports | personalization
4 | How likely would use a personalized news service? | Response Percent | Response Count
| Extremely likely | 25.9% | 7
| Very likely | 33.3% | 9
| Moderately likely | 29.6% | 8
| Slightly likely | 3.7% | 1
| Not at all likely | 7.4% | 2
5 | If our new personalized news service were available today, how likely would you be to use it instead of competing services currently available from other sources? | Response Percent | Response Count
| Extremely likely | 14.8% | 4
| Very likely | 33.3% | 9
| Moderately likely | 33.3% | 9
| Slightly likely | 11.1% | 3
| Not at all likely | 7.4% | 2
6 | If you are not likely to use a personalized news service, why not? | Response Percent | Response Count
| Do not need a service like this | 11.8% | 2
| Do not want a service like this | 11.8% | 2
| satisfied with competing services currently available | 23.55% | 4
| cannot pay for a service like this | 11.8% | 2
| Not willing to pay for a service like this | 41.2% | 7
7 | How important is personally preferred news content when accessing news online? | Response Percent | Response Count
| Extremely important | 11.1% | 3
| Very important | 22.2% | 6
| Moderately important | 40.7% | 11
| Slightly important | 14.8% | 4
| Not at all important | 11.1% | 3
8 | What would make you more likely to use a personalized new service? | Easy-to-use, free | It is free | to have the features mentioned above, or at least to get as close as possible | If I had more time and /or reading it became a part of my routine as reading the newspaper used to be. | Having all my favorit channels in one news feed. | ease of us | Easy setup. | Automated news requirement profile that changes with ongoing requirements | I decide my sources | KNowing news source reliable and centre left liberal comment | I am interested in news from the justice system. Particularly the Supreme court and the new laws r garding IRS rulings. | Personal layout
9 | If our new service were available today, how likely would you be to recommend it to others? | Response Percent | Response Count
| Extremely likely | 15.4% | 4
| Very likely | 30.8% | 8
| Moderately likely | 30.8% | 8
| Slightly likely | 15.4% | 4
| Not at all likely | 7.7% | 2

## OAP_Report
Submitted Report