## Sheet1
| Task | Deadline | Status | Comment | Estimated hours | Actual hours spent | Person
Mock-up |  |  |  |  | 10 | 3
| Set up Easel account | 2012-10-10 |  |  | 1 | 1 | GC
| Create Fliptab space | 2012-10-11 |  |  | 1 | 1 | GC
| Example 1: Broadsheet | 2012-11-14 |  |  | 2 | 1 | VP
| Example 2: Mid market | 2012-11-14 |  |  | 3 | 0 | VP
| Example 3: Tabloid | 2012-11-14 |  |  | 3 | 0 | GC
| Testing | 2012-11-14 |  |  | 1 | 0 | GC
Interviews & Survey |  |  |  |  | 16 | 2 | VP/AA/GC
| Create Evaluation Plan | 2010-10-17 |  |  | 1 | 1 | GC
| Create User Test Written Instructions | 2010-10-17 |  |  | 1 | 1 | GC
| Create Survey | 2010-10-15 |  | Need mock-up | 3 | 0 | VP/GC
| Conduct tests | 2010-10-19 |  | Need mock-up | 10 | 0 | VP/AA/GC | 5 tests each
| Conduct online survey | 2010-10-19 |  | Need mock-up | 1 | 0 | VP/AA/GC
Submit |  |  |  |  | 5 | 0
| Write-up results | 2010-10-20 |  |  | 2 | 0 | VP/AA/GC
| Write-up report | 10/20/2012 |  |  | 2 | 0 | GC
| Submit assignment | 2010-10-21 |  |  | 1 | 0 | GC